## Slide 1
P6 4-port choke nozzle damaged. Replacement campaign Mar 2020
FCRBV closure time not meeting SCE PS. Study submitted to NOPSEMA Jan 2020
P8 SCSSV (refer: Well Integrity Dashboard)
DHG issues (refer: Well Integrity Dashboard/MTO 121856). Voltage to be lowered under eMOC 84083 during Subsea Controls Campaign Q2 2020
Prelude Subsea System Dashboard
TOPSIDE
SUBSEA
RISER/UMBILICAL
POWER/COMMS
HYDRAULIC
MEG
P4
P7
SPCU
HPU
ESDVS
MCS
UTAS
SFLS
RISER 5
RISER 6
RISER 7
RISER 8
FL1
FL2
FL4
FL3
P8 MEG filter housing damaged. Requires TWI to inject via ASL (long term integrity threat). WO 61151660
P1 MEG MOV failed. Requires manual operation in field. Repair scheduled in May 2020. WO 60994458
ESDV position indicators. Change under eMOC. 3oo4 completed
VGMS GRVs to be removed to allow continuous monitoring of riser annulus. Target Q4 2020. WO 60899023-6
EPU TPU issues. TEM rack power supply to be replaced during Subsea Controls Campaign Q2 2020. NWO 30317348
ASDs non-functional above 70 deg. eMOC to be developed
Riser 8 polymer coupon access fitting damaged since installation. Replacement during turnaround.
RBM
MEG
PME
PRODUCTION SYSTEM
DISTRIBUTION SYSTEM
PMW
CI
CHEMICAL
SWIVEL
VGMS
COMMENTARY
Current as at: 7/2/2020
CAPITAL SPARES
408
418
420
SCM
FM
1
2
P5
P3
P8
 |  | IN SERVICE, NO ISSUES
 |  | IN SERVICE, FAULTS
 |  | OUT OF SERVICE
 |  | UNDER PRESERVATION
FM 1 under repair at TFMC Darwin. Est. completion 15/2.
FM 2 under fabrication. Est. completion Apr 2021.
MPMM
MPMM
MPMM
MPMM
P1
EFLS
ESFL
IDENTIFIED
Dec 2019
Sep 2019
Sep 2019
Jul 2019
Dec 2019
Dec 2018
Jan 2020
Jul 2019
Early 2019
P6
PSDVS
ASD
RCVs [not in scope]